## Calcs
Fully Burdened Cost for one FTE for one sprint |  |  |  | 6400
`
Sprint | Headcount | Cost | Total Cost | (a) % of Investment | Total Delivered Value | (b) % Delivered Value | (c) Ratio
1 | 3 | 19200 | 19200 | 2.326% | 0 | 0% | 0%
2 | 4 | 25600 | 44800 | 5.426% | 0 | 0% | 0%
3 | 4 | 25600 | 70400 | 8.527% | 0 | 0% | 0%
4 | 5 | 32000 | 102400 | 12.4% | 0 | 0% | 0%
5 | 5 | 32000 | 134400 | 16.28% | 0 | 0% | 0%
6 | 5 | 32000 | 166400 | 20.16% | 0 | 0% | 0%
7 | 6 | 38400 | 204800 | 24.81% | 40 | 40% | 161.2%
8 | 6 | 38400 | 243200 | 29.46% | 40 | 40% | 135.8%
9 | 7 | 44800 | 288000 | 34.88% | 40 | 40% | 114.7%
10 | 7 | 44800 | 332800 | 40.31% | 70 | 70% | 173.7%
11 | 7 | 44800 | 377600 | 45.74% | 70 | 70% | 153.1%
12 | 7 | 44800 | 422400 | 51.16% | 70 | 70% | 136.8%
13 | 7 | 44800 | 467200 | 56.59% | 70 | 70% | 123.7%
14 | 7 | 44800 | 512000 | 62.02% | 90 | 90% | 145.1%
15 | 7 | 44800 | 556800 | 67.44% | 90 | 90% | 133.4%
16 | 7 | 44800 | 601600 | 72.87% | 90 | 90% | 123.5%
17 | 7 | 44800 | 646400 | 78.29% | 90 | 90% | 115%
18 | 7 | 44800 | 691200 | 83.72% | 90 | 90% | 107.5%
19 | 7 | 44800 | 736000 | 89.15% | 90 | 90% | 101%
20 | 7 | 44800 | 780800 | 94.57% | 90 | 90% | 95.16%
21 | 7 | 44800 | 825600 | 100% | 100 | 100% | 100%
|  |  | 825600 |  | 100

## Instructions
1 | Set the fully-burdened cost of one FTE for a single sprint. Example: 80 hours in sprint X 80 dollars per hour = 6,400
2 | Set the projected number of team members for each iteration.
3 | Set the cumulative value projected to be delivered for each sprint.
4 | At the end of each sprint, update the projection with the actual for the completed sprint. Also update projections for other sprints.